## Sheet1
Sprint | Week | Dates (Mon - Fri) | Task
1 | 0-1 | 26. Aug - 29. Aug | Office setup | Reverse engineering of E-STIM 2B device to identify its main functionality and study improvement possibilities
2 | 1-2 | 1. Sep - 5. Sep | Reverse engineering of E-STIM 2B device to identify its main functionality and study improvement possibilities
3 | 2-3 | 8. Sep - 12. Sep | Reverse engineering of E-STIM 2B device to identify its main functionality and study improvement possibilities
4 | 3-4 | 15. Sep - 19. Sep | Designing a prototype hardware platform for implementing extended functionality of E-STIM 2B.
5 | 4-5 | 22. Sep - 26. Sep | Designing a prototype hardware platform for implementing extended functionality of E-STIM 2B. | MCU firmware development
6 | 5-6 | 29. Sep - 3. Oct | Ordering prototype boards from China | Creating a prototype for Smartphone.
7 | 6-7 | 6. Oct - 10. Oct | Creating a prototype for Smartphone.
8 | 7-8 | 10. Oct - 17. Oct | Receiving prototype boards and assembly. | Prototype testing.
9 | 8-9 | 20. Oct - 24. Oct | Development of a housing that meets the requirements for comfortable and safe use | Making changes to the prototype board. Re-ordering.
10 | 9-10 |  | At this point, there should be a basic understanding of the project and existing developments from which we can finalize the firmware, software for mobile platforms, and refactor the board. Specific tasks will be added upon reaching sprint 10.
11 | 10-11
12 | 11-12
13 | 12-13
14 | 13-14
15 | 14-15
16 | 15-16
17 | 16-17
18 | 17-18
19 | 18-19
20 | 20-21
21 | 21-22
22 | 22-23
23 | 23-24